# Longden Parish Council Neighbourhood Plan Steering Group

# Meeting 16 – 2nd September 2024 Red Lion Pub, Longden Common, 7:30pm

# Minutes

- Present and apologies – Present; P Arnold, Chair, P Carter, K Lovegrove, Jonathan Lovegrove, P McDonald, Jos Lovegrove, C Higgins; Apologies; E Pierce Jenkins, N & J Ingham, W Sheffield

- Notes of meeting held 5th August 2024 (attached)- P McD commented that the employment notes 6.a.ii should make reference to the benefits to the community shop of using the Tankerville Arms as a business hub. The minutes were approved with this addition.

- Locality Grant – To note a second grant application has been approved to cover additional consultancy costs and one in-person visit -Total value of grants £10,000.  CH confirmed the additional grant money had been paid into the parish council account.  She reminded the group that the grant funds had all been allocated, with the majority being earmarked for consultant fees so any additional expenditure would require budget approval from the parish council.

- Planning Consultant – Meeting arranged on 12th September.  Parish tour from 11am followed by discussion in village hall (approx. 12pm – 2:30pm) then a walk to appreciate the traffic congestion at school pick-up times.  P Carter offered to collect the consultant from the station and drive round the parish, taking in key points of interest and concern.  P Arnold offered his car instead.

- Planning Training Opportunity – CPRE training session with Hannah Barter (Urban Vision Enterprise) on impact of new Government planning proposals – Tues 24th September 6-8pm (£15 per person) – Interest shown by several members of the committee so agreed to seek two places for the NP Steering Committee in addition to the two for the parish council.

- Housing Needs Assessment – Awaiting decision from Locality/AECOM (Post meeting update – Application has been approved and we await contact from AECOM on next steps)

- Technical Support –

  - Strategic Environmental Assessment - Awaiting screening opinion from Shropshire Council (early September).  Rosie Corner will be named contact at Shropshire Council

- Questionnaire – Summary and analysis of responses to date – Due to the extended deadline and the number of additional paper surveys to be input, this was deferred to the next meeting.  Total number of surveys completed to date = 87.  It was agreed to take down the post boxes but to leave the online survey open indefinitely.  Paper surveys to be input by 6 September by volunteers.  Original surveys to be returned to the Clerk after inputting.

- Stakeholder mapping and Engagement – Practical exercise – The group identified a number of stakeholder groups and considered how these might be approached.

  - Snowdrop Club – Women’s group – PC to approach

  - Primary School – J Ingham has offered to approach

  - Scouts & Hanwood Youth Club – R Evans

  - Looked after children – R Evans / Shropshire Youth Association – KL has a contact

  - Young people – Secondary schools / school bus companies to be approached to allow us to speak to school students.

  - Faith Groups – local Catholic group – PC; Anglicans – Rector of local church to be asked to speak to his congregation

  - Dog Walkers – Local puppy training club

  - Farmers / Landowners – Jos Lovegrove to compile a list of landowners surrounding Longden village

  - Hard to reach groups – These groups were considered to have low population levels within the parish but could potentially be reached through supporting organisations and charities

    - Low income – ‘Warm space’ at village hall

    - Disabled people

    - Elderly people – Coffee morning at village hall

    - Ethnic minorities

    - LGBTQ+

    - Single parents – Schools?

  - Businesses – Direct approach agreed to the new Community Shop Committee – PC;

Further approaches to the Farriers businesses had not generated any additional survey completions so it was proposed that separate letter asking about current restrictions and plans for business development would be more appropriate.  CH to prepare a draft for the next meeting.

  - Climate action groups – N & J Ingham

  - Others?

- Date of next meeting –7 October 2024

The meeting closed at 8:45pm